## Equipment Asset
No | S/N | Description | Family | BU | BU Line | Status | Owner Engineer | Asset |  |  | Job No | Asset_Group_ID | Asset_Group_Desc | Manufacturer | Asset_Owner | PM | PM PERIOD | CALIBRATION | CAL. PERIOD | CAL ID | CAL. SUPPLIER | Equip. Picture | Manual Doc Attachment | By Whom | Last Update | Remark
[8 empty] | RF ID | CO | EAM
1 | SZFIT0012 | BOOK3 ICT ATV32B BTOOTH ( EOL ) | BOOK3 | BU2 | Line 28 | ACTIVE | winner | 702370432 | - | - | 53255/08/12 | ICT | FIXTURE | PETRACARBON | Consigned | YES | 2 month | YES | 1 years | C206 | Berca | isi gambar | copy to folder based on ID | userID | datetime
2 | SDFFT0055 | BUS BOARD FCT TEST SHORT TESTER # 3 ( EOL ) | BUS BOARD | BU1 | Line 29 | ACTIVE | supri | 52435t35 | - | - | 53255/08/13 | FCT | FIXTURE | CUSTOMIZE | In-House | YES | 3 month | YES | 1 years | C222 | Multi
3 | SYFIT0039 | CARROS ICT 20000866 ( EOL ) | CARROS | BU3 | Line 30 | ACTIVE | yosef | 635636 | 10035808 | 896535 | 53255/08/14 | SIMPLE TEST | FIXTURE | SEICO |  | YES | 4 month | YES | 1 years | C245 | HTR
4 | USA312312 | CARROS ICT 20000868 ( EOL ) | CARROS | WAREHOUSE | - | STORED | nanang | 653657467 | 10035809 | 896536 | 53255/08/15 | EQUIPMENT | EQUIPMENT | SEICO |  | NOT REQUIRED | 5 month | YES | 1 years | C293 | HTR
5 | SYFIT0041 | CARROS ICT 20000870 ( EOL ) | CARROS | CUSTOMER SITE | - | EOL | bruce | 74674674u8585 | 10035810 | 896537 | 53255/08/16 | ICT | TESTER | SEICO |  | NO | 6 month | YES | 1 years | C287 | HTR
6 | SYFIT0042 | CARROS ICT 20000871 ( EOL ) | CARROS | BU1 | Line 33 | ACTIVE | steven | 5345345345 | 10035811 | 896538 | 53255/08/17 | FCT | TESTER | SEICO |  | YES | 7 month | NO | 1 years | C192 | HTR
7 | SYFIT0049 | CARROS ICT 20000624 ( EOL ) | CARROS | BU2 | Line 34 | UNKNOWN | ardi | 5345345365 | 10035820 | 896547 | 53255/08/18 | MODULE | EQUIPMENT | SEICO |  | YES | 8 month | YES | 1 years | C876 | HTR
Equipment Asset
1. Expandeble rows table viewer
Parent row : S/N, Description, Family, BU, BU Line, Status, Owner Engineer,RF ID,CO,EAM, Asset_Group_Description
Child row : other coloums with picture viewer, except Parent Row
2. Downloadable data table to doc.file and data package attachment as well
3. Viewer Dashboard.
STATUS (How many active?, stored?, EOL?, UNKNOWN?)
BU(how many in BU2, BU1, BU3, Warehouse,Customer site)
Asset (how many doesn't has CO number?, doesn't has EAM number?)
Total Data Row (how many Consigned?, In-House?)
4. Data Entry (Create,Edit based on per owner Engineer authorization, except for Admin )
5. If delete need Admin Only as Engineer request email. (delete activity which simple log)
6. user able to Uploaded and downloaded file based on selected S/N

## Spare Part Request
NO | Equip. ID/SN | Description | Picture Description | Family | ORDER QTY | RECEIVED QTY | REQUEST DATE | PRIORITY | STATUS | Close date | History Comment | Latest History attachment
1 | SZFIT0012 | Gas Spring |  | RSX |  | 40 | 2019-12-27 | High | Completed
2 | SDFFT0055 | Fixture Lock |  | Kala, Vega, Lxm |  | 80 | 2019-10-10 | High | In Progress
3 | SYFIT0039 | Refurbish ICT Fixture |  | RSX |  | 1 | 2020-01-27 | High | In Progress
4 | USA312312 | Socket OTS-20-1.27-01 |  | Kala, Vega, Lxm |  | 20 | 2020-01-13 | High | open
5 | SYFIT0041 | Receptacle for socket OTS-20-1.27-01 |  | Vega |  | 8 | 2020-01-13 | Medium | open

## Action Tracker
Test Engineering - Action Tracker
No | Action item | Purpose/Goal/Objectives | Start Date | Due Date | Responsible Person | Remarks | Before | After | Status
13 | Follow Up Engineer Verification of template Rod & Push Finger of ICT fixture | - supporting engineers pre-verification | 2019-11-20 | 15 Des 19 | Yosef HS | 12 Jan - '99.7% progressing of 324 ICT Fixtures |  |  | Completed
14 | Restoring Rod & Push Finger after Engineer Verification on template Rod & Push Finger of ICT fixture | - readiness completion of templete versus actual | 2019-11-20 | 15 Des 19 | Adi Damar | 11 Dec - Seek for Customer (SEMB) approval (P'Wahyudi) 12 Dec - 42 Fixtures still waiting on parts 20 Jan 20 - Proposing to P'Supriyono (SEMB) to buyoff but still haven't provided available time, |  |  | Completed
15 | Create Draft - Internal ICT Fixture Modification guide line for review | - supporting new procedure | 2019-10-16 | 2019-10-19 | Yosef HS |  |  |  | Completed
16 | Spectrum ICT Fixture refurbishing | - Restoring productivity due to long setup preparation and bad condition | 2019-07-31 | 2019-08-08 | Yosef HS | -. Waiting Send the adaptor base at 12 Dec 19 (LT=1 month) 12 Dec - sent to Test Service 13 Jan20 - Receive the adapter from supplier and report issue FixtureLock status. 14 Jan 20 - Buyoff engineer P'Agussanto and P'Irwan(TestService). Engineer release to run. |  |  | Completed
17 | Carros Fixture (Mirano & STB) Refurbish | - Restoring productivity due to long setup preparation and bad condition | 2019-08-13 | 2019-08-30 | Yosef HS | 28 Nov - 20000734 has been sent (LT=3 weeks) 17 Dec - Request update vendor update status, it's still waiting rubber fabricating and install. 23 Dec - 20000734 buyoff with engineers and 2 concerns, rubber and reduce gas spring strength force. (LT 2weeks) 23 Dec - 20000733 has been sent (LT=3weeks) 09 Jan 20 - Receive 20000733 from supplier 12 Feb 20- still waiting for 20000730 system time 5 Mar 20 RE: Acknowledgement PO 2203649846 APOLLO 20190920000146 --> GRN missing |  |  | In Progress
18 | Segregate and laping EOL fixtures | - Optimized rack capacities with active fixtures | 2019-12-04 | 2019-12-30 | Adi Damar | 1. ATV12P S1 #2 (52347/11/08 or SZFIT0004) 2. VFS15P S2C4 FP (53013/10/11 or SZFIT0020) 3. VFS15 MC S2C4 (53012/10/11 or SZFIT0021) 4. VFS15P S3C4 4.0KW (53015/10/11 or SZFIT0022) 5. VFS15P S3C4 2.2KW (53014/10/11 or SZFIT0023) 6. VFS15P S2C4 FCT (53016/10/11 or SZFFT0004) 7. VFS15P S3C4 4.0KW FCT (53018/10/11 or SZFFT0005) 8. VFS15P S3C4 2.2KW FCT (53017/10/11 or SZFFT0006) |  |  | Completed
19 | Create summary form of weekly Tester Report Progressing | - visibility of tester history and follow up | 2019-09-09 | 2019-09-09 | Winner |  |  |  | Completed
20 | Reduce preparation time to start a troubleshooting request | - optimize preparation time due to no communication tool. | 2019-09-09 | 2020-02-04 | Winner | 4 feb 20 P'Hari ready announce tester support request |  |  | Completed
21 | Repair MPU for containment replacement HP#30 | - Repair due to no available spare | 2019-11-25 | 2019-11-26 | Winner |  |  |  | Completed
23 | Non- VMI Spare part list | - set non-vmi visibility part of tester | 2019-12-02 | 2019-12-20 | Winner | 17 Dec still collecting data 20 Dec send to P'Bhageeth and P'Wahyudi |  |  | Completed
24 | Target outcome of 32 fixtures per daily Maintenance | - set man power versus target daily. | 2019-11-20 | TBA | Yosef HS | -. 20 Nov, As proposed, waiting man power 6 person (currently 2 person) '-. 27 Jan 20, 3 tech and 3 operator to PM shared with 3 conversion operators. |  |  | Completed
30 | 5 New Machince Setup | -. To add new machine in BU3 | 31 Des 19 | 2020-01-11 | Winner | - 31 Dec 19 Uncrating 3 machine -. 02 Jan 20, Prepare ESD Mat. -. 03 Jan 20, Pack 2 Bridging Tester and Vendor setup. -. 06 Jan 20 Keep tester parts. -. 08 Jan 20, Install antivirus and login calibrations -. 09 Jan 20, Backup 2 testers -. 14 Jan 20, Backup 2 testers -. 27 Jan 20, Backup 1 tester |  |  | Completed
31 | Restoration Fixture condition | -. To restore fixture condition | 2020-01-06 | 2020-02-06 | Adi Damar | -06 Jan 20, assign man power, but as discuss with pak Wahyudi, still waiting the effective date of implementation which related to conversion pick up and return by Support tech. -. 28 Jan 20 per shift, 1 operator will deliver and the support will help at the station line. use the rest to support maintenence. (Maintenance : 3 tech and 3 operator share with conversion task) |  |  | Completed
32 | Method to back up new agilent system win10 | -. To be able back up | 2020-01-08 | 2020-01-09 | Yosef HS | - Using Acronis |  |  | Completed
33 | Carting 2 bridging testers | -. Return back to keysight | 2020-01-08 | 2020-01-13 | Yosef HS | -. 9 Jan 20, Re-tie all packs '-. 13 Jan 20, transfer to shipping. |  |  | Completed
34 | Change Receptacles of S5 | -. P'Puji Request | 2020-01-11 | 2020-01-27 | Adi Damar | 1. ATV12F S1C2 # 2 (SZFIT0032) 2. ATV12F S1C2 # 1 (SZFIT0007) 3. ATV12F S1C1 C3 (SZFIT0008) 4. ATV12 S2 P F # 1 (SZFIT0006) 5. ATV12 S2 P F # 2 (SZFIT0030) 6. ATV12P S2S3 F3 (SZFIT0005) 7. PHXF IC2 2C2 (SZFIT0017) |  |  | Completed
35 | propose grand access to sentinel one 1. Rmiregistry.exe 2. Vservice.exe (vision Services) 3. Rmiserver.exe 4. Xvl.exe (Xvision 32-Bit Server) | -. To prevent sentinel one active the firewall so make tester can't bootup | 2020-01-08 | 2020-02-08 | Yosef HS | 14 Jan 20, IT creating SNC number 20 Jan 20 FollowUp P'Afdhal and ready GrandAccess by Sentinel One |  |  | Completed
36 | Combine HP#49 image for HP#33 | -. To replace error image HP#33 | 2020-01-14 | 2020-02-16 | Winner | -.16 Jan 20 re-image to rebackup, HP#33 up under monitor |  |  | Completed
37 | Assisting installation of action point 25 to Bellatrix (P'Lasimin) | -. Bellatrix enhancement on IC programming | 2020-01-16 | 2020-02-16 | Yosef HS |  |  |  | Completed
38 | List LineID and RFID Number (Fixed Asset Physical Inventory of tester) | -. Per Finance audit inventory request | 2020-01-20 | 2020-01-22 | Winner |  |  |  | Completed
39 | Investigation HP#28 | -. Resolving Intermitent, Pass Diagnostic but fail continuity on probes | 2020-01-27 | 2020-01-28 | Yosef HS | ASRU card is malfunction |  |  | Completed
40 | Verify Short Nail on Fixture RS3C | -. To verify short R207 | 2020-01-29 | 2020-01-29 | Yosef HS | -. Probes wiring is tally with the fixture consultant diagram. '-. The root cause is hidden solder ball in probes PCBA plate hose (tech. Aldo found it) |  |  | Completed
41 | Registering E-XING | - to support E-XING fixture part order | 2020-01-27 | 2020-02-07 | Yosef HS |  |  |  | Completed
42 | Prepare SEMB Asset | - Support SEMB Request | 2019-12-11 | 2020-02-29 | Yosef HS | 31 Jan 20 send to P'Wahyudi for review (RE: Fixture Verification by SCH) |  |  | Completed
43 | Prepare Implementation CA: 1. Check Gas Spring Function 2. Input Push Finger and Rod size 3. Sort Fixture based on PN PCBA | - Support SEMB Request | 2019-12-11 | 2020-02-29 | Yosef HS | 4 Feb 20 it's checked, waiting implementation of qty comparison |  |  | Completed
44 | Get Keysight help to resolve Short PinCard on upgraded HP from series 3 to series 5 | - Resolve suspected disharge issue | 2020-01-24 | 2020-02-29 | Yosef HS | 24 Jan 20, info keysight service. 30 Jan 20, P'martahi send affected test program 5 Jan 20, Ivan send discharge file for series 5 |  |  | Completed
45 | Setup GR23=GR28 | -.Enlarge capability and backup tester | 2020-02-05 | 2020-02-05 | Yosef HS | -. Add in 2 recycle pincard to GR23 |  |  | Completed
78 | Enhanced Pin Guide and Re-Probing Probes in dashboard | - set predict replacement plan period and probes type & Qty | 2020-07-16 | 2020-08-16 | Yosef HS |  |  |  | In Progress
79 | Enhanced ICT PM system in dashboard | - set PM ICT system & information | 2020-07-16 | 2020-08-16 | Yosef HS | 1. 16 Jul 20 Entry plan PM schedule |  |  | In Progress
Completed / Closed
On Schedule & Progressing
Not on Schedule / Not Completed
Plan

## Enhancement
Nama | Grade | Major | Project | Intent Period
Febriana Manalu | D3 | IT | Equipment Asset system | 8 Month
Ibnu Mas ud | D3 | Electronica | Equipment Asset system | 4 Month
Supriyanto | SMK | Power Electric | Tester PM & System Data | 8 Month